## PSP
/bank-attention/PSP0
PSP0 Project Plan Summary
Project Owner | Jhon SebastiÃ¡n Ijaji Ortiz
Start Date | 2020-09-19 17:10
Completion Date | 2020-09-30 23:09 |  |  |  | Completed: ☑
Keywords
Language
Time in Phase (min.) | Plan | Actual | To Date | To Date %
Planning |  | 0.020139 | 0.020139 | 2.3%
Design |  | 0.077083 | 0.077083 | 8.8%
Code |  | 0.62292 | 0.62292 | 71.1%
Compile |  | 0.083333 | 0.083333 | 9.52%
Test |  | 0.072222 | 0.072222 | 8.25%
Postmortem |  | 0 | 0 | 0%
Total | #VALUE! | 0.87569 | 0.87569
Defects Injected |  | Actual | To Date | To Date %
Before Development |  | 0 | 0 | 0%
Planning |  | 0 | 0 | 0%
Design |  | 0 | 0 | 0%
Code |  | 1 | 1 | 50%
Compile |  | 1 | 1 | 50%
Test |  | 0 | 0 | 0%
Total Development |  | 2 | 2
Defects Removed |  | Actual | To Date | To Date %
Planning |  | 0 | 0 | 0%
Design |  | 0 | 0 | 0%
Code |  | 1 | 1 | 50%
Compile |  | 1 | 1 | 50%
Test |  | 0 | 0 | 0%
Total Development |  | 2 | 2
After Development |  | 0 | 0
PSP materials copyright © 2018 Carnegie Mellon University, licensed under CC BY 4.0.